## Sheet1
Stakeholder Communication and Complaints Register Project: Beryl Solar Farm
Date | Time | Method of contact (phone, letter, email) | Stakeholder Name | Details | Received by | Action taken by Downer (or why no action was taken) | Date issue closed
2018-08-07 | 13:10 | Phone | Anonymous | Query regarding commencement of Construction Works prior to DPE Approval | DPE - B.Schultz - N.Roworth | Downer Rep met State Department Rep on Site to discuss. Only Test Piling had been undertaken - in accordance with Development Consent. | 2018-08-08
2018-08-23 | 1:30 | Phone (Hotline) | Allan Griffin | Complaint regarding Flashing lights operating past 18:00 | Hotline - N.Roworth | Downer Project Manager made contact with complainant 23/08/2018 and notified Flashing Lights will not be operating past 18:00. This requirement communicated across Downer Leadership Team within Weekly Meeting 23/08/2018 11:30am. Email across Project Leadership Team notifying Flashing Lights not to be used after 18:00 & Compound Lights to be switched off by last person on site. | 2018-08-23
2018-08-29 | 21:06 | Text - N.Roworth | Allan Griffin | Is it necessary to have the generator and things still going at this tim of night | N.Roworth | Communication between Downer and First Solar with agreement for Downer Compound Generator to be switched off by last Downer person on site until a Sea Container is placed to deflect noise from the Stakeholders residence. | 2018-08-30
2018-09-03 | 17:32 | Phone Msg (T.Best, First Solar) | Allan Griffin | Voice Message: "What is this Fluro Orange mesh for? Are you trying to piss me off? | Tom Best (First Solar) | T.Best rang Allan at 18:31 and explained it was for sedimentation control and is required to be installed throughout the construction period as per Enviromental Management requirement. | 2018-09-03
2018-10-16 | 23:59 | Email | Dennis Armstrong | Query regarding westerly view from property at Black Lead Lane, Gulgong. | Bjorn Schultz (First Solar) | B.Schultz conducted a site assessment and it is not expected to have views of the solar farm from this property. | 2018-10-30
2018-11-03 | 9:17 | Phone - N Roworth | Lisa Swan | Phone call equiry as to what time piling operations are on Weekends? Lisa thought weekends were all quiet works. Nathan informed Lisa the orginal DA time is 8am - 1pm only on Saturdays and quiet works outside of that time | N.Roworth | Nathan informed Lisa that there are more Piling Rigs than scheduled to finish the Piling Sooner - in Approx 7 weeks (prior to Christmas) Nathan Apologised and said he understood her point of view. Ensure Operations of Piling are within the specified times - 1st piling started today at 8:01am | 2018-11-03
2018-12-06 | 16:41 | Phone - N Roworth | Lisa Swan | Phone call regarding Vehicles being seen speeding and cutting Corners at Beryl Road onto Castlereagh Highway. Same coming onto Beryl Road from Castlereagh Highway | N.Roworth | Nathan thanked Lisa for letting him know. A Downer representative was sent directly to the Corner of Beryl Road and Castlereagh Highway that afternoon to observe driving behavours. On this particular day there had been an accident on the Castlereagh Highway Bridge, there were alot of Maintenance Vehicles, Safety Vehicles and road closed signs present, no reckless behavour observed this Day, so may not be a true reflection. A Downer representative will continue to attend the Corner for observations on random days for both morning and afternoon traffic observations | Ongoing monitoring
2018-12-07 | 10:15 | Phone - N Roworth | Doug Marsh | Reported Trucks missing the Beryl Site enterance and performing U Turns in front of this Residence - an inspection was made | N.Roworth | Downer to send a representative to rectify grass damage caused by a Truck performing a U Turn | 2018-12-10
2019-01-16 | 14:58 | Phone | Darryl Benson | Please return my call regarding the dust from this dirty filthy Beryl Solar Farm, it is choking us and has been dreadful ever since you turned up. "Phone Number". You better start watering up there. | N.Roworth | N.Portess spoke with Darryl 17:10 with apology for the dust issues and notification an additional 40,000Litre watercart had been on site for the day to assist in controlling the dust. This would be continuing throughout the heat wave and as required. Darryl was informed the re-seeding has taken place with ongoing watering - hoping for rain to assist in germination. It was noted the high temperatures in combination with windy conditions this afternoon had exacerbated dust issues. N.Potess asked Darryl if he had been contacted previously in association with BSF. Darryl attended some early meetings associated with the Project however hadn't been concated by anyone associated. Darryl advised to contact N.Portess with any further issues. | 2019-01-16